## ActionItems
ACTION ITEMS
PRACTICE NAME |  |  | Last Updated: | 2020-04-19 |  |  | Next Meeting: | 2020-04-20 15:30
ACTION ITEM | RANK | PRIORITY | OWNER | ASSIGNED | DUE | DONE | STATUS | NOTES
Review Practice SOP's | 5 | HIGH |  | 2020-04-15 | 2020-05-11 |  | Not Started
Recalls: Past Due | 5 | HIGH |  | 2020-04-20 | 2020-05-06 |  | Not Started
Online Eyewear Order Portal | 5 | HIGH |  | 2020-04-20 | 2020-04-24 |  | Not Started
Yourlens.com/Lensferry CL Online Orders | 5 | HIGH |  | 2020-04-20 | 2020-04-22 |  | Not Started
Fee Slip Corrections for Medicare visits | 5 | HIGH |  | 2020-04-20 | 2020-04-30 |  | Not Started
Practice re-opening SR Announcement | 5 | HIGH |  | 2020-04-20 | 2020-04-24 |  | Not Started
Staff meeting prior to practice re-open to review new procedures | 5 | HIGH |  | 2020-04-20 | 2020-04-23 |  | Not Started
Reduce doctor schedule time to ensure social distancing | 5 | HIGH |  | 2020-04-20 | 2020-04-20 |  | Not Started
Reduce or eliminate patient form scanning aligning with Intakeq.com | 5 | HIGH |  | 2020-04-20 | 2020-04-30 |  | Not Started
Sanitizing Process of rooms, equipment, pc's, phones, eyewear etc | 5 | HIGH |  | 2020-04-20 | On going |  | Not Started
Doctor/tech handoff to optician | 4 | MEDIUM |  | 2020-04-20 | 2020-04-20 |  | Not Started
HIPAA | 2 | MEDIUM |  | 2020-04-15 | 2020-05-01 |  | Not Started
Front Desk Check-in Process | 4 | MEDIUM |  | 2020-04-21 | 2020-04-21 |  | Not Started

## Help (hidden)
HELP
About
This template provides a simple way to track action items assigned to different members of a group. The template includes two different ways to show priority, using Low/Medium/High or a numeric Rank. You can use them both or delete the column you don't want to use.
Editing the Drop-Down Lists
To edit the drop-down list in the Priority column, select the cells you want to edit then go to Data > Data Validation.
If you change the list of items in the Priority drop-down list, then you may need to edit the conditional formatting rule(s) as well.
Conditional Formatting
To edit conditional formatting rules, go to Conditional Formatting > Manage Rules and select "This Worksheet" to see and edit all the rules.
When you mark the Done column with a check, a conditional formatting rule will change the font in that row to gray.